ORACLE CLOUD INFRASTRUCTURE — FUSION ENABLEMENT

Enterprise Architect Playbook

A reusable, engagement-agnostic playbook for enabling greenfield Oracle Fusion Cloud Applications (ERP, EPM, HCM, CX) with Oracle Integration Cloud (OIC), Autonomous Database (ATP), and Fusion Data Intelligence (FDI) on OCI.

Scope: Greenfield Oracle Fusion SaaS + OCI PaaS under one tenancy, weighted to the OCI Platform / Enterprise Architect role, with explicit hand-off boundaries to the Fusion functional/security and data workstreams.

How to use this template: This is a generic model. Replace every <placeholder> with engagement specifics (tenancy name, pod names, partners, legacy system, CostCenter list). Appendix E lists every placeholder to tailor. Sections 3–4 are a reusable governance-review checklist to run against whatever governance a customer has already drafted.

Prepared by: OCI Platform / Enterprise Architect  |  v1.0 (generic template)  |  Classification: template — mark per engagement

# Contents at a Glance

1. Executive summary and how to use this playbook

2. The two control planes — what you are actually governing

3. Governance foundations to establish

4. Common governance gaps and corrections (review checklist)

5. Phase roadmap overview

6. Day 0 — before you touch anything

7. DISCOVER (weeks 1–3)

8. PLAN (weeks 2–6)

9. ASSESS (weeks 4–7)

10. BUILD (weeks 6–20+, in waves)

11. MANAGE (steady-state operating model)

12. OPTIMIZE (continuous)

13. First 30 / 60 / 90 days as OCI Platform Lead

14. Decision gates and open questions register

Appendix A — Target compartment tree (template)

Appendix B — IAM policy statements (valid OCI syntax)

Appendix C — Governance tag schema

Appendix D — RACI skeleton

Appendix E — Tailoring checklist (placeholders to fill)

# 1. Executive Summary and How to Use This Playbook

This playbook enables a greenfield Oracle Cloud program: the customer has procured Oracle Fusion Cloud Applications (ERP, EPM, HCM, CX) as SaaS, plus OCI infrastructure services — Oracle Integration Cloud (OIC), Autonomous Database (ATP), and Fusion Data Intelligence (FDI) — under a single Oracle Cloud tenancy. The common greenfield pattern assumed here is that an incumbent non-Oracle ERP is retired at Fusion go-live and only master data (plus opening balances) migrates — no transactional history — which greatly simplifies the data workstream and removes the need for a permanent coexistence architecture. Where a legacy system must coexist, treat that as an added workstream and adjust the migration and integration sections accordingly.

The playbook does two things. First, it gives a reusable method to validate and correct whatever OCI governance the customer has drafted (compartments, IAM, tags, Cloud Guard / Security Zones) against Oracle best practice for a combined Fusion + OCI tenancy. Second, it lays out a sequenced path from Day 0 through Discover, Plan, Assess, Build, Manage, and Optimize — weighted to the OCI Platform Lead role, with clear hand-off boundaries to the Fusion functional/security and data workstreams.

### The five things to internalize on Day 0

- Fusion SaaS is not inside your VCNs. The Fusion pods are Oracle-managed and reached over the Oracle Services Network (OSN). Your VCNs, subnets, and network policies govern OIC, ATP, FDI access paths, and partner-built apps only. The SaaS compartments hold service handles/subscriptions, not infrastructure.

- There are two governance planes. OCI IAM never controls who can see a Fusion invoice, worker record, or opportunity. Fusion application security (job/duty/data roles, security profiles, data access sets, SoD) is a separate plane with a separate owner. Your job is the OCI plane plus the identity bridge between the two.

- HCM is the identity source of record. The worker model in HCM feeds downstream user provisioning across all pillars. Identity/SSO architecture (corporate IdP federation → OCI Identity Domains → Fusion) is a critical-path platform deliverable that you co-own.

- Master-data quality is the critical path. With no transactional migration, the data workstream is compact but unforgiving: chart of accounts, suppliers, customers, items, workers, and opening balances must be right. Plan 2–3 mock conversion cycles. Your platform provides the machinery (OIC, ATP staging, object storage, FBDI/HDL pipelines).

- Governance must be live before builders arrive. Partners and internal teams will build integration-layer components in the tenancy. Compartments, groups, policies, tags, budgets, logging, and Cloud Guard must be operational before Dev access is granted — retrofitting governance is 10x harder.

# 2. The Two Control Planes — What You Are Actually Governing

Everything sits in one tenancy, but it splits into two fundamentally different planes. Confusing them is the single most common failure mode in Fusion + OCI programs.

| Dimension | Plane 1 — OCI (customer-managed) | Plane 2 — Fusion SaaS (Oracle-managed) |
| --- | --- | --- |
| What lives here | OIC instances, ATP database(s), FDI (OAC + its managed ADW), VCNs/subnets/gateways, object storage, API Gateway, Vault/KMS, partner-built apps, logging/monitoring | Fusion pods per pillar and environment: ERP, EPM, HCM, CX (e.g., fa-<realm>-<pod> for prod / dev / test) |
| Access control | OCI IAM: identity domains, groups, compartments, policies, tags, Security Zones | Fusion security: job/duty/abstract/data roles, security profiles, data access sets, GL segment-value security, SoD |
| Network | Your VCNs; private endpoints; Service Gateway to OSN; DRG/VPN/FastConnect if hybrid connectivity is needed | No customer VCN presence. Reached over OSN / public endpoints with allow-listing; integrations call REST/SOAP over TLS |
| Patching | You schedule ATP maintenance; OIC patched by Oracle in defined windows | Oracle quarterly updates (e.g., 25C/25D/26A) — you plan regression testing, not the patch itself |
| Owner | OCI Platform Lead + network/security teams | Fusion functional/security team + SI partner; you own the identity bridge and integration touchpoints |
| Governance artifact | OCI governance model / rule sets (reviewed per §3–4) | Role design workbook, SoD matrix, access certification — a separate workstream |

### Where the procured PaaS actually sits

- OIC — the integration backbone. Connects to Fusion over OSN (REST/SOAP adapters), not VCN peering. Runs FBDI/HDL orchestration for data loads, real-time integrations for partners, and hosts the File Server. Governed by an OIC standards annex (see G9).

- ATP — customer-managed autonomous database with a private endpoint in an App-Processing subnet. Legitimate uses: OIC staging/persistence, custom app data, cross-reference/lookup stores, FDI data-transform augmentation targets. It never backs Fusion — the Fusion database is Oracle-managed and invisible to you.

- FDI — Fusion Data Intelligence = OAC plus an Oracle-managed ADW provisioned into the tenancy with prebuilt ERP/HCM/CX analytics pipelines. FDI's ADW is a different database from your procured ATP (different owner, lifecycle, patching). Give FDI its own Analytics compartment.

# 3. Governance Foundations to Establish

These are the patterns a well-run Fusion + OCI tenancy should adopt (and that you should preserve and formalize where a customer has already drafted them, rather than re-litigate):

- Environment-first compartmentalization. Applications/{Dev1, Dev2, Test, Prod} aligned to Fusion environments — not one compartment per application — is the correct optimization for isolation, IAM control, standardization, and cost observability.

- Vendor separation with delegated control. Per-partner sub-compartments (Partner A / Partner B / Internal → Fusion-Integrations) with 'manage all-resources in their own compartment' plus scoped 'use' grants for network/LB/object storage. Vendor A cannot see Vendor B.

- Centralized networking in Shared-Services. One VCN per environment owned by grp-network-ops, consumed cross-compartment via scoped 'use subnets where target.vcn.name=…' policies. Prevents drift and duplication.

- Least-privilege group model. grp-network-ops, grp-app-devs, grp-app-admins, grp-db-admins, grp-security, grp-cost-audit, grp-analytics, breakglass and read-only-global elevation groups; zero direct user grants; no workloads in root.

- Tag-driven governance. A Governance tag namespace (Owner, CostCenter, Environment, Application, DataClassification, Partner, WorkloadType, Lifecycle), tag defaults per compartment, tag-driven Cloud Guard detections and Security Zones.

- Graduated security stance. Cloud Guard auto-remediate in Dev, alert+selective in Test, alert+escalate in Prod; Security Zones on Applications:Prod, Analytics, and Vault/KMS; secrets/KMS centralized in Shared-Services.

- Infrastructure-as-code from day one. The landing zone is Terraform; hand-built consoles do not survive four environments and a restructure. Use Oracle's CIS-aligned landing-zone modules as accelerators, adapted to the approved blueprint.

# 4. Common Governance Gaps and Corrections (Review Checklist)

Run this checklist against the customer's drafted governance. These fourteen gaps recur across greenfield Fusion + OCI programs; 'Owner' indicates who should close each — several deliberately fall outside the OCI platform scope and must be assigned, not absorbed.

| # | Common gap | Correction | Priority |
| --- | --- | --- | --- |
| G1 | IAM policy uses 'Deny' — which does not exist. Drafts write 'Deny group … to manage …'. OCI IAM is default-deny and additive; such rules do not compile and the implied protection does not exist. | Re-express every 'deny' as absence-of-allow plus guardrails: scope allows narrowly, use policy conditions (e.g., where target.compartment.name != 'Prod'), and enforce hard guardrails with Security Zones. See Appendix B. | Critical |
| G2 | Fusion application-security plane omitted. Most real access risk (who can pay an invoice, see salaries, change a supplier bank account) lives in Fusion RBAC, which OCI never touches. | Stand up a separate Fusion Security workstream: role design (job/duty/data/abstract), security profiles, data access sets + GL segment-value security, SoD rules and periodic access certification. Owner: functional security team. | Critical |
| G3 | Identity architecture undefined. Domains named but no target topology, no federation design, no join between HCM (worker source) and account provisioning. | Design identity domains early: default domain for OCI platform admins only; workforce federation to corporate IdP (SAML/OIDC) for one SSO across Fusion, FDI/OAC, OIC, and Console; SCIM/HDL provisioning from HCM; MFA everywhere; 2 breakglass accounts excluded from federation, vaulted, and alarmed. | Critical |
| G4 | SaaS scope incomplete. Compartment tree lists only some pillars; entitlement (Prod + Test + Dev1–n per pillar) not fully recorded. | Extend SaaS handles to all procured pillars (ERP, EPM, HCM, CX); record every pod (URL, release, purpose, refresh source) in an environment register. Confirm licensed CX pillars and whether Payroll is in HCM scope (both are decision gates, §14). | High |
| G5 | FDI placement/identity unresolved. FDI treated as an ERP sub-resource; it is OAC + an Oracle-managed ADW with its own lifecycle. | Create a top-level Analytics compartment for FDI. Provision Prod first; add non-prod later. Keep FDI's ADW distinct from the procured ATP. Map FDI data security to Fusion roles; plan ERP/HCM/CX subject areas. | High |
| G6 | ATP role confusion risk. A 'Databases' node exists but its purpose is unstated — inviting scope creep ('put Fusion data in it'). | Charter ATP explicitly: OIC staging, custom/partner app persistence, integration cross-reference data. Private endpoint only. Never a Fusion backing store; no bulk replication of Fusion transactional data outside FDI. | High |
| G7 | Unsafe tag policy. 'Allow any-user to create instance … where request.resource.tag…' grants creation rights to every principal if tags are present — the opposite of least privilege. | Delete the any-user rule. Enforce tagging via tag defaults (required, per-compartment) plus group-scoped conditional allows, and Cloud Guard detections for missing/incorrect tags. Add CostCenter and Partner as required defaults. | High |
| G8 | Security Zone coverage too narrow. Applied only to Applications:Prod, leaving FDI's ADW (replicated sensitive data) and Vault/KMS (crown jewels) unprotected. | Extend Security Zones (or custom recipes) to the Analytics and Vault/KMS compartments. Keep the graduated stance elsewhere. | Medium |
| G9 | OIC-internal governance missing. Governance stops at the compartment; OIC is itself a multi-tenant workspace needing standards (File Server security, folder structure, env promotion, MFT). | Adopt an OIC governance annex: project/connection naming, role model per env (ServiceDeveloper in Dev, ServiceDeployer promotion in Test/Prod), CI/CD via OIC APIs, File Server folder + user/group standards before higher environments, error-handling/logging patterns. | Medium |
| G10 | Network model vs reality. VCN-per-environment designed as if apps live there, but Fusion is OSN-reached; nothing yet on Service Gateway, NAT, private endpoints, DNS, or egress control. | Per VCN: Service Gateway (all OSN services), NAT for controlled egress, no internet gateway in Prod, private endpoints for ATP/OIC where supported, NSGs per tier, DNS zones, explicit allow-listed egress. Document that Fusion traffic transits OSN, not peering. | Medium |
| G11 | Residual root/legacy debris. Workspace/DIS policies at root; transitional compartments coexist with the target tree. | Fold into Assess-phase remediation: re-home policies to owning compartments, execute the move plan (export → inventory → create target → baseline policies → dry-run → move one → validate), and retire transitional compartments. | Medium |
| G12 | No budgets, quotas, or cost guardrails. A cost-audit group may exist but nothing defines budgets, alert thresholds, or compartment quotas. | Budgets per top-level compartment with 70/90/100% alerts; compartment quotas to zero-out expensive shapes in Dev/Sandbox; scheduled cost reports keyed to CostCenter/Partner tags. | Medium |
| G13 | Logging/audit retention undefined. A governance compartment 'serves audit/logging' but no retention, sink, or SIEM decision is recorded. | Set audit retention to maximum; create Logging/Log Analytics sinks in Governance; service + flow logs on all VCN subnets; decide SIEM export (streaming to the customer SOC) during Plan. | Medium |
| G14 | Environment refresh & release management absent. Nothing governs Fusion P2T refreshes, quarterly-update regression windows, or how OIC/FDI/ATP track a refreshed pod. | Publish an environment & release calendar: quarterly Fusion updates per pod, P2T refresh schedule, post-refresh integration re-pointing runbook (endpoints, credentials, FDI re-baseline), and code-freeze windows around cutover. | High |

Bottom line: adopt an environment-first compartment model with four common amendments — add an Analytics compartment (G5), extend SaaS to all pillars (G4), extend Security Zones (G8), and rewrite all pseudo-deny rules (G1) — then bolt on the three governance layers most often missing: identity (G3), Fusion security (G2), and OIC-internal standards (G9).

# 5. Phase Roadmap Overview

Phases overlap deliberately; durations assume a 9–12 month program to first go-live. FDI non-prod, full EPM build-out, and MFT/SFTP replacement typically land post-go-live.

| Phase | Indicative timing | Platform-lead focus | Exit criteria |
| --- | --- | --- | --- |
| Day 0 | Week 0 | Access, artifacts, stakeholder map, cadence, risk/decision registers | You can see everything; registers live |
| Discover | Weeks 1–3 | Tenancy/entitlement audit, environment & integration inventory, current-state findings | Signed-off current-state pack + confirmed entitlements |
| Plan | Weeks 2–6 | Target architecture blueprint, landing-zone design, identity design, environment/release calendar, migration & integration strategies | Architecture board approves blueprint + decision gates dispositioned |
| Assess | Weeks 4–7 | Policy dependency analysis, compartment move plan, security/readiness assessment, mock-conversion readiness | Move plan rehearsed; gaps have owners and dates |
| Build | Weeks 6–20+ | Landing-zone waves 0–4: guardrails → structure/network → PaaS provisioning → FDI → integration & data pipelines; cutover rehearsals | Prod landing zone certified; mocks 2–3 clean; cutover runbook signed |
| Manage | From first Dev handover | Operating model, monitoring, patch/refresh calendar, access certification, support tiers, hypercare | Steady-state ops with SLOs; hypercare exited |
| Optimize | Continuous post-go-live | FinOps, Cloud Advisor, posture score, FDI expansion, MFT/SFTP replacement roadmap | Quarterly optimization review installed |

# 6. Day 0 — Before You Touch Anything

### 6.1 Access and artifacts to obtain (first 48 hours)

- Tenancy access: OCI Console access with (initially) read-all; confirm who holds the tenancy Administrator role and where breakglass credentials live today.

- Oracle contract picture: subscription documents, CSI numbers, universal-credit vs SaaS line items, entitlement confirmation (Prod + Test + Dev1–n per pillar; OIC/ATP/FDI SKUs and sizing; BYOL positions).

- Environment handles: URLs and admin contacts for every Fusion pod, OIC instances, existing ATP, Visual Builder Studio, any data-integration workspaces.

- My Oracle Support: access to the support identifier; visibility of open SRs and the Fusion release schedule per pod.

- The governance corpus: compartment/IAM strategy docs, rule-set drafts, OIC/File Server notes, plus any Terraform/scripts already applied to the tenancy.

- Existing identity state: identity-domain list, current users/groups, any federation already configured, how partner users authenticate today.

### 6.2 Stakeholder map and cadence

- Identify owners for: tenancy admin, network, security/SOC, Fusion functional leads per pillar, data/MDM owner, each partner lead, Oracle account team (CSM / domain specialists), and the program manager.

- Install cadence: weekly architecture working session, weekly platform build stand-up (once Build starts), fortnightly architecture board for decisions, and a single decision log + risk register (start them Day 0 — seed with §14).

- Agree the RACI boundary explicitly: you own the OCI plane and the identity bridge; the functional team owns Fusion RBAC/SoD; the data owner owns master-data quality; partners build inside the guardrails you set (Appendix D).

### 6.3 Day-0 quick wins (safe, high-signal)

- Turn on / verify Cloud Guard at tenancy level (detect-only), confirm audit-log retention is maximized, and snapshot an export of all current IAM policies and compartments as the Assess-phase baseline.

- Create the decision-gate register (§14) and get dates against the two that block everything else: identity topology (G3) and Payroll-in-scope (HCM).

# 7. DISCOVER (Weeks 1–3)

Goal: a signed-off current-state pack. Nothing is built yet; you are creating the factual baseline every later phase depends on.

### 7.1 Tenancy and platform audit

- Full inventory: compartments (including any transitional tree), all IAM policies (export verbatim), identity domains, dynamic groups, tag namespaces, budgets, quotas, Cloud Guard state, logging config, existing VCNs and orphaned resources.

- Flag debris now: root-level workspace policies; any policies written 'in tenancy' that should be compartment-scoped; unused resources in sandbox/data-integration compartments.

- Region strategy: confirm home region, FDI/OIC/ATP region alignment with the Fusion pods, and capture any latency/data-residency constraints for later DR design.

### 7.2 Subscription and environment verification

- Reconcile procured vs provisioned: per pillar (ERP, EPM, HCM, CX) confirm which of Prod/Test/Dev1–n exist, their releases, and the quarterly-update schedule; confirm FDI status; capture OIC edition/message-pack sizing and ATP OCPU/storage/licensing.

- Build the environment register (living artifact): pod → purpose → release → refresh source → connected OIC/FDI/ATP instances → owning team.

### 7.3 Integration and application discovery

- Interface inventory: every planned integration — banks (payments/statements), tax, e-invoicing/statutory, payroll interfaces (if in scope), CX↔ERP flows, EPM data loads, third-party systems, and each partner component — with direction, pattern (REST/SOAP/FBDI/HDL/extract), volume, and frequency.

- Review each partner footprint: what they deploy (compute? functions? OIC artifacts?), what network/LB/object-storage access they truly need — this validates or trims the drafted vendor policies.

- Assess current OIC usage: projects, Dev File Server configuration (project-specific user security, OIC/<project> folders), and Visual Builder Studio environments — input to the OIC governance annex (G9).

### 7.4 Data discovery (support role for the platform lead)

- Master-data census from the legacy system: COA + segment values, ledgers/BUs/legal entities, suppliers, customers, items/products, bank accounts, workers, jobs/positions/grades, cost centres, projects, asset masters — owner, volume, and quality per object.

- Platform angle: where staging happens (ATP schemas), how files move (object storage vs OIC File Server), and whether legacy history is wanted in FDI's ADW custom schemas for reporting after retirement.

### 7.5 Discover-phase deliverables

- Current-state architecture pack; entitlement reconciliation; environment register v1; integration inventory v1; master-data census; debris/risk list feeding Assess.

# 8. PLAN (Weeks 2–6)

Goal: an approved target blueprint and the strategies that govern Build. Run Plan in parallel with late Discover — do not serialize.

### 8.1 Target platform blueprint (core deliverable)

- Adopt an environment-first compartment model: root → Governance, Shared-Services (Networking, Identity-Integrations, Shared-Tools, Vault/KMS), Applications {Dev1, Dev2, Test, Prod} × {Partner A, Partner B, Internal, PaaS}, SaaS handles {ERP, EPM, HCM, CX}, Analytics (FDI), Sandbox. Full tree in Appendix A.

- Network design per environment VCN: Service Gateway (OSN), NAT, no IGW in Prod, Integration-Shared-Subnet + App-Processing-Subnet (+ optional Vendor-Isolated-Subnet if the gate in §14 requires), NSGs, private DNS, ATP private endpoints.

- Identity design (G3): domain topology, IdP federation (SAML/OIDC), SCIM/HDL provisioning from HCM, MFA policy, admin tiers, breakglass procedure. One SSO across Fusion + OIC + FDI/OAC + Console.

- IAM policy set: write the full rule set with valid syntax (Appendix B), scoped per group per compartment, conditions instead of pseudo-denies.

- Tag schema finalization (Appendix C) with required defaults incl. CostCenter and Partner; budgets and quotas per compartment.

### 8.2 Environment and release management plan (G14)

- Map Fusion envs to platform envs: which OIC instance serves which pod; FDI Prod against Fusion Prod (non-prod FDI later); ATP per env or shared-with-schema-isolation in Dev.

- Publish the calendar: quarterly Fusion update windows per pod, P2T refresh cadence, post-refresh re-pointing runbook, code-freeze rules.

### 8.3 Integration architecture and OIC governance annex (G9)

- Patterns catalogue: FBDI/HDL batch via OIC + object storage; REST/SOAP real-time; ERP business events where applicable; error-hospital pattern; naming standards; connection/credential management via Vault.

- OIC standards: project structure, role model per env, CI/CD promotion pipeline (OIC APIs + Git), File Server folder/user/group standards agreed before Test/Prod promotion.

### 8.4 Data migration strategy (platform view)

- One-time load, master data + opening balances (opening trial balance as GL journal). Tooling: FBDI (ERP/SCM/Procurement), HDL (HCM), REST/file import (CX), ADFdi for small sets. 2–3 mock cycles with entry/exit criteria; reconciliation reporting via FDI/OTBI; legacy freeze-and-extract plan.

### 8.5 Security, compliance and Fusion-security workstream charter (G2)

- Cloud Guard target state per env; Security Zones on Applications:Prod, Analytics, Vault/KMS; SIEM export decision; vulnerability/posture reporting.

- Charter the Fusion security workstream with the functional team: role design method, SoD ruleset, access certification cadence — you review the identity touchpoints only.

# 9. ASSESS (Weeks 4–7)

Goal: prove the transition from a transitional tenancy to the target blueprint is safe, and that the organization is ready to build.

- Policy dependency analysis. For every exported policy: hard-coded compartment paths, 'in tenancy' over-scoping, references that break when compartments move. Resources do not move with compartments — IAM evaluation paths change; cross-compartment grants may need updates.

- Integration/tooling dependency check. Terraform state, CI/CD pipelines, monitoring and cost tools, and any external tooling that references OCIDs or compartment paths.

- Compartment move plan. Export all policies → identify dependencies → inventory OIC instances, API gateways, object storage, functions, identity integrations → create target compartments → apply baseline policies → dry-run validation → move ONE low-risk compartment → validate access, workloads, automation → then batch the rest.

- Security assessment. Cloud Guard findings triage, public-exposure scan (object storage, open 22/3389/0.0.0.0/0, public IPs), IAM over-permission review, MFA coverage, breakglass validation.

- Readiness assessment. Skills (is a dedicated OCI engineer needed on the customer side — validate), partner onboarding readiness, data-owner readiness for mock 1, decision gates dispositioned or dated.

- Assess deliverables. Move runbook (rehearsed), remediation backlog with owners, security baseline report, readiness scorecard, and the go/no-go to start Build waves.

# 10. BUILD (Weeks 6–20+, in Waves)

Everything below is Terraform-first: hand-built consoles do not survive four environments and a restructure. Stand up a platform repo + state backend (object storage with versioning) in Wave 0 and treat the landing zone as code from day one. Consider the Oracle-published CIS-aligned landing-zone modules as accelerators, adapted to the approved blueprint.

## Wave 0 — Guardrails first (before any builder access)

- Tag namespace + required tag defaults; groups (incl. grp-analytics, grp-breakglass-admins, grp-readonly-global) mapped to identity domain / IdP groups; baseline policy set from Appendix B.

- Governance compartment: audit retention max, Logging/Log Analytics sinks, Cloud Guard tenancy-wide (detect), budgets + alerts per top-level compartment, compartment quotas for Dev/Sandbox.

- Identity: federation to corporate IdP, MFA enforcement, admin tiers, breakglass accounts vaulted + alarmed.

## Wave 1 — Structure and network

- Create the target compartment tree (Appendix A); execute the compartment move runbook from Assess; retire transitional compartments; re-home any workspace policies (G11).

- Build VCN-Dev1/Dev2/Test/Prod with subnets, Service Gateway, NAT, NSGs, private DNS; Vault/KMS in Shared-Services; Security Zones on Prod + Analytics + Vault.

## Wave 2 — PaaS provisioning

- OIC instances per environment in Applications:{env}:PaaS; ATP with private endpoint in App-Processing-Subnet; object storage buckets (per env, per purpose, lifecycle policies); API Gateway where needed.

- Apply the OIC governance annex: projects, roles per env, connections via Vault, CI/CD promotion pipeline, File Server standards (Dev pattern reviewed before promotion).

- Onboard partners: partner groups scoped to their compartments; verify Vendor A cannot see Vendor B; hand over 'paved-road' docs (how to get a subnet, a bucket, a secret, a connection).

## Wave 3 — Analytics (FDI)

- Provision FDI (Prod pipeline first) in the Analytics compartment; connect to Fusion Prod source; activate ERP/HCM/CX subject areas per license; map FDI data security to Fusion roles; plan legacy-history custom schemas in ADW if retained.

## Wave 4 — Integration and data migration execution

- Build integrations per the patterns catalogue; error-hospital + alerting live before mock 1.

- Mock conversions: mock 1 (structure/quality shakeout), mock 2 (full-volume timed), mock 3 (dress rehearsal incl. opening balances + reconciliation sign-off). Master-data quality is the critical path — hold the gate.

- Cutover: freeze legacy, final extract → transform (ATP staging) → load (FBDI/HDL/REST) → reconcile → open Fusion; hypercare rota agreed; legacy to read-only then decommission per retention policy.

# 11. MANAGE (Steady-State Operating Model)

- Operating model. Platform team runs Governance/Shared-Services/Analytics; app teams and partners operate inside Applications:{env}; SaaS run handled by functional + SI with Oracle. Publish SLOs and a support-tier matrix (P1 integration failure vs P4 sandbox request).

- Observability. OCI Monitoring alarms (OIC error rates, ATP CPU/storage, budget burn), Logging Analytics dashboards, OIC integration-level monitoring + error hospital, FDI pipeline health checks, Cloud Guard problems routed to the SOC.

- Patch and refresh calendar. Fusion quarterly updates (customer tests, Oracle patches) with regression windows per pod; OIC Oracle-managed patching windows acknowledged; ATP maintenance schedules set; post-P2T re-pointing runbook executed every refresh (G14).

- Access lifecycle. Joiner/mover/leaver via HCM → IdP → domains; quarterly access certification on both planes (OCI groups AND Fusion roles/SoD); breakglass use alarmed and reviewed; partner access time-boxed and re-attested.

- Backup/DR. ATP automatic backups + long-term where needed; object storage versioning/replication by classification; OIC design-time export to Git as recovery position; document RTO/RPO per service and the (accepted) dependency on Oracle for SaaS DR.

- Cost management. Monthly cost review keyed to CostCenter/Partner tags; budget alerts triaged in platform stand-up; showback to vendors/teams.

# 12. OPTIMIZE (Continuous)

- FinOps. Cloud Advisor recommendations monthly; ATP auto-scaling tuned to real load; storage lifecycle tiering; delete transitional debris; renegotiate/resize subscriptions at renewal with real consumption data.

- Security posture. Track Cloud Guard security score quarterly; expand Security Zone recipes as maturity grows; periodic red-team-style review of vendor compartments.

- Platform roadmap items. OIC File Server as the standard file-exchange platform and eventual legacy MFT/SFTP replacement (evaluate after go-live stability); FDI non-prod environment; additional FDI subject areas and custom KPIs; EPM build-out (EPBCS/FCCS/ARCS/Narrative Reporting); Dev3/Dev4 activation when parallel project streams demand it.

- Continuous governance. Quarterly governance review: policy drift vs Appendix B, tag compliance rate, unused resources, environment register accuracy, decision-log hygiene.

# 13. First 30 / 60 / 90 Days as OCI Platform Lead

| Horizon | Outcomes you own | Proof it happened |
| --- | --- | --- |
| Day 30 | Day-0 checklist complete; current-state pack signed off; entitlements reconciled; governance corrections (§4) accepted by the architecture board; decision gates G3 (identity) and HCM-payroll dated; registers running | Baseline export archived; board minutes accepting the amended compartment model; environment register v1 published |
| Day 60 | Target blueprint approved; IAM policy set written and peer-reviewed; environment/release calendar published; Assess complete — move runbook rehearsed on one compartment; Terraform repo + Wave 0 guardrails live in Dev scope | One compartment moved and validated; Cloud Guard + budgets + tag defaults active; partners still have zero prod access |
| Day 90 | Waves 1–2 substantially built: target tree live, transitional tree retired, VCNs + Vault operational, OIC Dev/Test provisioned under the governance annex, ATP private-endpoint live, partner onboarding done on paved-road docs; FDI provisioning scheduled; mock-1 machinery ready | Builders building inside guardrails; first FBDI/HDL pipeline demonstrated end-to-end in Dev; mock 1 date committed |

# 14. Decision Gates and Open Questions Register

Seed the program decision log with these. Each needs an owner and a date; several block Build waves.

| # | Decision | Why it matters | Blocks |
| --- | --- | --- | --- |
| D1 | Identity domain topology + IdP federation design (Okta/Entra, SAML vs OIDC) | Single SSO across Fusion/OIC/FDI/Console; provisioning source from HCM | Wave 0; all user onboarding |
| D2 | Is Payroll in HCM scope? | Major swing: parallel runs, statutory reporting, pay calendars, extra interfaces | HCM timeline; integration inventory |
| D3 | Which CX pillars are licensed/in scope (Sales/Service/CPQ)? | Determines CX pods, subject areas, integration patterns | CX workstream; FDI subject areas |
| D4 | FDI non-prod timing (Prod-first confirmed?) | Cost vs test coverage for analytics changes | Wave 3 scope |
| D5 | Vendor-isolated subnet vs shared Integration subnet | Isolation vs network sprawl | Wave 1 network build |
| D6 | Legacy history retention: FDI/ADW custom schemas, archive, or drop? | Reporting continuity vs cost; affects decommission plan | Wave 3–4; decommission runbook |
| D7 | OIC File Server as standard file platform; legacy MFT/SFTP replacement roadmap | Security/folder standards must precede Test/Prod | Wave 2 OIC annex; Optimize roadmap |
| D8 | ATP sizing/licensing (BYOL?), shared-vs-per-env in non-prod | Cost and isolation trade-off | Wave 2 provisioning |
| D9 | SIEM/SOC export of audit + Cloud Guard events | Compliance posture; SOC integration effort | Wave 0 logging design |
| D10 | Dev3/Dev4 activation criteria per pillar | Entitlement exists; cost/refresh overhead if activated early | Environment register; refresh calendar |

# Appendix A — Target Compartment Tree (Template)

No workloads in root. Replace <tenancy> and partner names per engagement.

<tenancy> (root) — no workloads in root

├─ Governance — IAM policy home, audit/logging sinks, security tooling

├─ Shared-Services

│    ├─ Networking — VCN-Dev1 / VCN-Dev2 / VCN-Test / VCN-Prod (SGW, NAT, NSGs, DNS)

│    ├─ Identity-Integrations — IdP federation apps, SCIM plumbing

│    ├─ Shared-Tools

│    └─ Vault-KMS — secrets & keys (Security Zone)

├─ Applications

│    ├─ Dev1 ── Partner-A / Partner-B / Internal (Fusion-Integrations) + PaaS (OIC, ATP, API GW)

│    ├─ Dev2 ── same pattern

│    ├─ Test ── same pattern

│    └─ Prod ── same pattern (Security Zone)

├─ SaaS — service handles only (Oracle-managed platforms)

│    ├─ ERP (Prod, Test, Dev1–n)      ├─ EPM (Prod, Test, Dev1–n)

│    ├─ HCM (Prod, Test, Dev1–n) — identity source of record

│    └─ CX  (Prod, Test, Dev1–n; licensed pillars per D3)

├─ Analytics — FDI (OAC + Oracle-managed ADW), Prod first (Security Zone)

└─ Sandbox — data-team experiments; quota-capped

# Appendix B — IAM Policy Statements (Valid OCI Syntax)

OCI IAM has no Deny keyword: access is default-deny and policies are additive. Every 'Deny …' from a draft is achieved by scoping allows narrowly and adding guardrails (Security Zones, quotas). Representative set — finalize in Plan §8.1.

Root / breakglass

Allow group grp-security to read all-resources in tenancy Allow group grp-breakglass-admins to manage all-resources in tenancy Allow group grp-readonly-global to read all-resources in tenancy

Network (replaces pseudo 'Deny … virtual-network-family')

Allow group grp-network-ops to manage virtual-network-family in compartment Shared-Services Allow group grp-network-ops to read all-resources in tenancy Allow group grp-app-devs to use subnets in compartment Shared-Services where target.vcn.name = 'VCN-Dev1' # No other group receives a virtual-network-family MANAGE grant — that IS the deny.

App dev / promotion (replaces 'Deny devs in Prod')

Allow group grp-app-devs to manage all-resources in compartment Applications:Dev1 Allow group grp-app-devs to manage all-resources in compartment Applications:Dev2 Allow group grp-app-admins to manage all-resources in compartment Applications:Test Allow group grp-app-admins to manage all-resources in compartment Applications:Prod Allow group grp-app-admins to read all-resources in tenancy

Vendors (Partner-A shown)

Allow group grp-vendor-a to manage all-resources in compartment Applications:Dev1:Partner-A Allow group grp-vendor-a to use subnets in compartment Shared-Services where target.subnet.name = 'Integration-Shared-Subnet' Allow group grp-vendor-a to use load-balancers in compartment Applications:Dev1:Partner-A Allow group grp-vendor-a to use object-family in compartment Applications:Dev1:Partner-A # Replicate per partner per environment; Vendor A cannot see Vendor B.

Analytics, DB, security, cost

Allow group grp-analytics to manage all-resources in compartment Analytics Allow group grp-db-admins to manage database-family in compartment Applications:Prod Allow group grp-db-admins to read database-family in compartment Applications:Test Allow group grp-security to manage cloud-guard-family in tenancy Allow group grp-security to manage vaults in compartment Shared-Services:Vault-KMS Allow group grp-cost-audit to read all-resources in tenancy Allow group grp-cost-audit to read usage-reports in tenancy

Tag governance (replaces the unsafe any-user rule)

Allow group grp-security to manage tag-namespaces in tenancy Allow group grp-security to manage tag-defaults in tenancy Allow group grp-app-admins to manage instance-family in compartment Applications where request.resource.tag.Governance.CostCenter is not null # Primary enforcement = required tag defaults per compartment; conditional allows are the backstop; Cloud Guard detects gaps.

# Appendix C — Governance Tag Schema

| Tag (Governance.*) | Allowed values / pattern | Drives | Required? |
| --- | --- | --- | --- |
| Owner | apps-team, integration-team, db-team, vendor-a, vendor-b, platform-team | Ownership, incident routing | Yes (default per compartment) |
| CostCenter | Finance-aligned list (IT-Shared, ERP-Program, HCM-Operations, Project-###) | Budgets, showback, cost reporting | Yes |
| Environment | Dev1, Dev2, Test, Prod (matches compartment default) | Tag-driven policies, Cloud Guard env-mismatch detection | Yes (default per compartment) |
| Application | Fusion-ERP, Fusion-HCM, Fusion-CX, Fusion-EPM, Integration-Platform, Analytics, Shared-Services | Cost rollups, audit clarity | Yes |
| DataClassification | Public, Internal, Confidential, Restricted | Security Zones, Cloud Guard, access restrictions | Yes |
| Partner | Internal, Partner-A, Partner-B | Vendor spend attribution, isolation checks | Yes |
| WorkloadType | Integration, Application, Database, Network, Security, Analytics | Policy targeting, reporting segmentation | Recommended |
| Lifecycle | Active, Planned, Deprecated | Cleanup automation | Recommended |

# Appendix D — RACI Skeleton

A = Accountable, R = Responsible, C = Consulted, I = Informed. Finalize in Day 0 / Discover.

| Activity | OCI Platform Lead | Fusion Functional / Security | Data / MDM Owner | Partners |
| --- | --- | --- | --- | --- |
| OCI landing zone, IAM, network, tags, guardrails | A/R | I | I | C |
| Identity domains, IdP federation, SSO, breakglass | A/R | C | I | I |
| Fusion RBAC, security profiles, SoD, access certification | C | A/R | I | C |
| OIC platform + governance annex (incl. File Server) | A/R | C | C | R (build) |
| ATP / object storage / API gateway provisioning | A/R | I | C | C |
| FDI provisioning + security mapping | A/R | C (role mapping) | C | I |
| Master data extraction, cleansing, quality gates | C (machinery) | C (rules) | A/R | R (build) |
| Mock conversions + cutover runbook | R (platform) | C | A | R |
| Environment & release calendar (updates, P2T) | A/R | C | I | C |
| Cost management & optimization | A/R | I | I | I |

# Appendix E — Tailoring Checklist (Placeholders to Fill)

Before issuing this playbook for a specific engagement, replace every placeholder below and confirm the assumptions. This is what turns the generic template into an engagement artifact.

| Placeholder / assumption | Replace with | Notes |
| --- | --- | --- |
| <tenancy> | The OCI tenancy name / OCID | Appears in the compartment tree and policies |
| <realm> / pod names | Actual Fusion pod identifiers per pillar/env | Record in the environment register (§7.2) |
| Legacy ERP | The incumbent system name and its fate | Confirm retire-at-go-live vs coexistence — changes migration & integration scope |
| Partner-A / Partner-B | Actual SI/integration partner names | Drives vendor compartments, groups, and policies |
| Pillars in scope | ERP / EPM / HCM / CX (and CX sub-pillars) | Confirm licensing (D3) and Payroll-in-HCM (D2) |
| Environments | Dev1..Devn / Test / Prod actually entitled | Dev3/Dev4 activation is a decision gate (D10) |
| CostCenter / Owner values | Finance-aligned lists | Populate the tag schema (Appendix C) |
| IdP | Corporate identity provider (Okta / Entra / other) | Federation protocol SAML vs OIDC (D1) |
| Region(s) | Home region + DR region | Align FDI/OIC/ATP to the Fusion pods' region |
| SIEM / SOC | Customer security operations target | Audit + Cloud Guard export decision (D9) |
| Program timeline | Actual dates per phase | The 9–12 month roadmap is indicative only |

This playbook is a generic template synthesized from a project-specific Oracle Cloud Enablement Enterprise Architect Playbook. Validate every recommendation against current Oracle documentation and the specific tenancy before execution.